## Read Me
Lubist – Web QA Checklist
Scope | Website (customer, vendor portal, RM portal – Next.js) and the Admin Panel.
Where to test | STAGING only. Never production – payments and emails are real there.
How to use | Work top to bottom in 'Checklist'. Do the P1 rows first; the E2E rows are the most important.
Status column | Pick from the dropdown: Not run / Pass / Fail / Blocked / N/A.
On Fail | Add a row in 'Bug Log' and put its Bug ID in the checklist 'Bug ID / Notes' column.
Yellow cells | Columns for you to fill in: Status, Tested on, Tester, Bug ID / Notes, Automate?
Priority | P1 = must pass before release · P2 = important · P3 = nice to have.
Automate? | Mark Yes on flows worth automating later (start with the E2E P1 rows).
Summary | The 'Summary' tab updates automatically from the Status column.
Full guide | See the Word document 'Lubist QA Handover Guide' for URLs, accounts, and known 'not a bug' behaviours.

## Checklist
ID | Module | App | Role(s) | Scenario | Steps | Expected result | Priority | Status | Tested on | Tester | Bug ID / Notes | Automate?
EX-00 | (example) | Website | Customer | Example: how to fill a row | Steps are already written – just follow them. | Compare what you see with this column. | P1 | Fail | 2026-09-22 | Tester name | BUG-001 – total wrong after coupon | Yes
E2E-01 | End-to-end flows | RM Portal + Admin + Vendor Portal | RM → Admin → Vendor | New salon onboarding (full chain) | 1. RM logs in (/login/rm) → Add Salon → fill all steps with a REAL owner email you can open → Submit. 2. Admin Panel → Pending Salons → open the request → Approve. 3. Open owner inbox → click registration link → set password. 4. Vendor logs in (/login/vendor) → pay registration fee (Razorpay test). 5. Open the website /salons as a guest. | Request shows in RM Submissions as Pending, then Approved. Owner gets the email. After payment, vendor dashboard unlocks. Salon appears in public salon list. | P1 | Not run
E2E-02 | End-to-end flows | Admin Panel + RM Portal | Admin → RM | Admin creates a Relationship Manager | 1. Admin Panel → Users → Create User, role = Relationship Manager. 2. Check RM Management page. 3. Log in as the new RM at /login/rm. | RM appears in RM Management. RM can log in and sees RM dashboard (not customer/vendor pages). | P1 | Not run
E2E-03 | End-to-end flows | Website + Vendor Portal + Admin | Customer → Vendor → Admin | Book a service and see it reach the vendor | 1. As vendor, make sure salon has active services. 2. As customer, open the salon → select service(s) → Book → pick date & slot → add to cart. 3. Cart → Checkout → pay with Razorpay test. 4. Check /account/bookings. 5. As vendor, open Bookings → find it → Confirm → later Complete. 6. Customer refreshes /account/bookings. Admin → Appointments. | Booking confirmation page shows correct salon/service/date/amount. Booking appears in vendor Bookings + dashboard 'Today' (if today). Status changes reflect for the customer. Admin sees it in Appointments. | P1 | Not run
E2E-04 | End-to-end flows | Website + Admin | Customer → Admin | Buy a product | 1. /products → open a product → Add to cart. 2. Product cart (/cart/products) → change quantity → Checkout → pay (Razorpay test). 3. Check /account/orders. 4. Admin Panel → Product Orders → update order status. | Totals update with quantity. Order confirmation shown. Order listed in customer Orders and Admin Product Orders; status change visible to customer. | P1 | Not run
E2E-05 | End-to-end flows | Vendor Portal + Website | Vendor → Customer | Vendor coupon applied at checkout | 1. Vendor → Coupons → create coupon (e.g. 10% off, min order). 2. As customer, open that salon: offer should show on salon card/detail. 3. Add services to cart → apply code → checkout. 4. Vendor deactivates coupon → customer tries again. | Discount matches coupon rules (min order, max discount). Amount charged in Razorpay = discounted total. Deactivated coupon is rejected with a clear message. | P1 | Not run
E2E-06 | End-to-end flows | Admin Panel + Website | Admin → Customer | Admin (platform) coupon | 1. Admin → Coupons → create coupon (try a first-time-user coupon too). 2. Customer applies it at cart. | Coupon works on eligible orders only; first-time coupon rejected for a customer who already booked. | P2 | Not run
E2E-07 | End-to-end flows | Vendor Portal + Website | Vendor → Customer | Vendor runs a salon-wide promo | 1. Vendor → Run Promo → set % and dates → Apply. 2. Open the salon as customer. 3. Vendor applies a second promo. | Discounted prices show on salon services. Old promo moves to 'Past Promotions'. Promo and coupon do not stack (bigger discount wins). | P2 | Not run
E2E-08 | End-to-end flows | Website + Vendor Portal | Customer → Vendor | Customer cancels a booking | 1. Customer → /account/bookings → Cancel an upcoming booking. 2. Vendor checks Bookings. | Booking moves to Past/Cancelled for customer; vendor sees status Cancelled. | P1 | Not run
E2E-09 | End-to-end flows | RM Portal + Admin | RM → Admin → RM | Rejected salon request is fixed and resubmitted | 1. RM submits a salon. 2. Admin → Pending Salons → Reject with a reason. 3. RM → Submissions → Rejected tab → Edit & Resubmit. 4. Admin approves. | Rejection reason visible to RM. Resubmitted request returns to Pending. RM score/leaderboard updates after approval/rejection. | P2 | Not run
E2E-10 | End-to-end flows | RM Portal + Admin | RM → Admin → Buyer | Regular buyer (B2B) onboarding | 1. RM → Add Salon → choose Regular Buyer type → submit. 2. Admin approves ('Approve Buyer'). 3. Buyer completes registration and logs in. | Buyer sees 'Business Profile' (no public salon). Buyer does NOT appear in the public salon list. Buyer can buy products. | P2 | Not run
E2E-11 | End-to-end flows | Website + Admin | Customer → Admin | Review after completed booking | 1. Vendor marks a booking Completed. 2. Customer opens the feedback email link → submits rating/review. 3. Open the salon page and /account/reviews. | Review saved once (link shows 'already submitted' on reopen). Review shows on salon page. | P2 | Not run
E2E-12 | End-to-end flows | Website + Admin | Guest → Admin | Partner-with-us and Careers leads | 1. Submit /partner-with-us form. 2. Submit a /careers application. 3. Admin → Partner Requests and Career Applications. | Success message on the website. Both entries appear in Admin with the submitted details. | P2 | Not run
E2E-13 | End-to-end flows | Admin Panel + Website | Admin → Guest | Admin content shows on website (banners, blog) | 1. Admin → Banners → add an active banner. 2. Admin → Blog → publish a post with FAQs. 3. Open website home and /blog. | Banner shows in home carousel; deactivating hides it. Blog post and FAQ section visible. (If blog is hidden, check Admin → Feature Flags.) | P2 | Not run
AUTH-01 | Auth | Website | Guest | Sign up with email | Sign up with a real inbox → try to log in before confirming → confirm via email → log in. | Before confirming: clear message asking to confirm email. After confirming: login works. | P1 | Not run
AUTH-02 | Auth | Website | Customer | Login / logout (email + password) | Log in → refresh several pages → logout → press browser Back. | Stays logged in on refresh with no flicker/flash of logged-out UI. After logout, account pages redirect to login. | P1 | Not run
AUTH-03 | Auth | Website | Customer | Login with phone OTP | Login → Phone tab → Indian number → enter OTP. Try wrong OTP. | Correct OTP logs in; wrong OTP shows error. New number goes to profile completion. | P2 | Not run
AUTH-04 | Auth | Website | Customer | Forgot / reset password | Forgot password → email link → set new password → log in with it. | Reset works; old password no longer works. | P1 | Not run
AUTH-05 | Auth | Website | Vendor / RM | Portal login pages | Log in at /login/vendor and /login/rm with correct and wrong-role accounts. | Each role lands on its own dashboard; wrong role shows a clear error. | P1 | Not run
AUTH-06 | Auth | Website | Any | Role protection | As customer, open /vendor and /rm URLs directly. As guest, open /account. | Access denied (not found page) or redirect to login. No data leaks. | P1 | Not run
AUTH-07 | Auth | Website | Any | Already logged in | While logged in, open /login. | Redirected to your dashboard/home. | P3 | Not run
PUB-01 | Public website | Website | Guest | Home page | Open home; set/change location; click banners and category shortcuts. | Page loads without errors; banners, salons and products show; links work. | P1 | Not run
PUB-02 | Public website | Website | Guest | Salon list: search & filters | /salons → search by name, filter by city/category/gender, 'near me', pagination. Refresh with filters. | Results match filters; filters survive refresh (they are in the URL). Empty state when no results. | P1 | Not run
PUB-03 | Public website | Website | Guest | Salon detail page | Open a salon: services, opening hours, offers, reviews, related salons, call/email links. | All sections load. Hours match the salon's settings. Invalid salon URL shows 404 page. | P1 | Not run
PUB-04 | Public website | Website | Guest | Products list & detail | /products → filter/paginate → open product → related products. | Price, sale price, stock state correct. 'Add to cart' asks guest to log in. | P1 | Not run
PUB-05 | Public website | Website | Customer | Favourites | Heart a salon from list/detail → check /account/favorites → un-heart. | Favourite saved and removed correctly. | P2 | Not run
PUB-06 | Public website | Website | Guest | Static pages & 404 | About, FAQ, Privacy, Terms, Delete-account, random bad URL. | All load; 404 page has working links. | P3 | Not run
CART-01 | Cart & checkout | Website | Customer | Service cart edits | Add services from one salon → remove one → clear cart → add again. | Totals and item counts update instantly and after refresh. | P1 | Not run
CART-02 | Cart & checkout | Website | Customer | Slot selection | At checkout pick today, a future date and a closed day of the salon. | Only valid slots shown; closed days have no slots; past times today not offered. | P1 | Not run
CART-03 | Cart & checkout | Website | Customer | Payment failure / cancel | Start checkout → close Razorpay popup; then try a failed test payment. | No booking is confirmed; user can retry; clear message shown. | P1 | Not run
CART-04 | Cart & checkout | Website | Customer | Price breakdown | Check subtotal, discount, convenience fee and total on cart, checkout and Razorpay popup. | Same total everywhere; amount charged equals the total shown. | P1 | Not run
ACC-01 | Customer account | Website | Customer | Account home | Open /account with and without bookings/orders. | Shows upcoming booking, recent orders, favourites; sensible empty states. | P2 | Not run
ACC-02 | Customer account | Website | Customer | Bookings list | Upcoming vs Past tabs; cancel allowed only for pending/confirmed. | Completed/cancelled/no-show bookings cannot be cancelled. | P1 | Not run
ACC-03 | Customer account | Website | Customer | Profile edit | Change name/gender/age; add/verify phone via OTP; reload. | Changes persist after reload. | P2 | Not run
VEN-01 | Vendor portal | Vendor Portal | Vendor | Dashboard | Open /vendor. Click every card, quick action and sidebar item. | Numbers match real bookings; every link opens the right page and you can navigate back via the sidebar. | P1 | Not run
VEN-02 | Vendor portal | Vendor Portal | Vendor (unpaid) | Payment gate | Log in as a vendor who has not paid the registration fee. | Dashboard asks to pay; after test payment the dashboard unlocks and /vendor/payment redirects away. | P1 | Not run
VEN-03 | Vendor portal | Vendor Portal | Vendor | Add services (4-step wizard) | Services → Add → gender → category → sub-category → enter several services (name, price, duration) → save. | All services saved and listed; they appear on the public salon page. | P1 | Not run
VEN-04 | Vendor portal | Vendor Portal | Vendor | Edit / deactivate a service | Edit price & duration; deactivate a service; search and filter the list. | Changes show on public salon page; inactive service not bookable. | P1 | Not run
VEN-05 | Vendor portal | Vendor Portal | Vendor | Manage bookings | Bookings → filter by status/date, search → open details → Confirm → Complete; try No-show. | Status updates persist and are visible to the customer. (Vendor has no Cancel button by design.) | P1 | Not run
VEN-06 | Vendor portal | Vendor Portal | Vendor | Salon profile | Edit description, hours, facilities, address, location → Save → reload. Try Cancel. | Saved changes persist and show on public page; Cancel discards changes. | P1 | Not run
VEN-07 | Vendor portal | Vendor Portal | Vendor | Coupons CRUD | Create (with and without 'Valid From'), edit, deactivate. | All actions succeed; deactivated coupon no longer offered to customers. | P2 | Not run
RM-01 | RM portal | RM Portal | RM | Dashboard | Open /rm; check stats, needs-attention, recent submissions, rank. | Counts match Submissions page; links open correct filtered lists. | P2 | Not run
RM-02 | RM portal | RM Portal | RM | Save salon as draft & resume | Add Salon → fill some steps → Save Draft → Drafts → open → continue → submit. Delete another draft. | Draft reopens on the same step with all data (incl. address with commas). Delete removes it. | P1 | Not run
RM-03 | RM portal | RM Portal | RM | Submission validation | Try submitting without required fields / agreement doc / cover image. | Clear validation errors; nothing submitted. | P2 | Not run
RM-04 | RM portal | RM Portal | RM | Submissions, profile, leaderboard | Status tabs + search; edit profile name/phone; leaderboard Top 10/20/50. | Filters correct; profile saves after reload; own rank highlighted. | P3 | Not run
ADM-01 | Admin panel | Admin Panel | Admin | Login & dashboard | Log in to Admin Panel; open every sidebar page once. | Every page loads without errors or blank screens. | P1 | Not run
ADM-02 | Admin panel | Admin Panel | Admin | Users | Search/filter users; create user of each role; edit a user. | New user can log in with the role given. | P1 | Not run
ADM-03 | Admin panel | Admin Panel | Admin | Salons | Search salons; view details; activate/deactivate a salon. | Deactivated salon disappears from public website; reactivating brings it back. | P1 | Not run
ADM-04 | Admin panel | Admin Panel | Admin | Service categories | Add/edit a category or sub-category. | Shows up in the vendor Add Service wizard. | P2 | Not run
ADM-05 | Admin panel | Admin Panel | Admin | Products | Create product with images, price, sale price, stock; edit; deactivate. | Changes reflected on /products and product detail page. | P1 | Not run
ADM-06 | Admin panel | Admin Panel | Admin | Appointments & product orders | Filter appointments; update product order status. | Lists match real data; status change visible to customer. | P2 | Not run
ADM-07 | Admin panel | Admin Panel | Admin | RM management | Open an RM → edit profile/notes → view score history. | Changes saved; score history matches approvals/rejections. | P2 | Not run
ADM-08 | Admin panel | Admin Panel | Admin | System config & feature flags | VIEW ONLY unless the dev team asks: check fees/config pages and feature flags load. | Pages load. Do not change payment keys or fees without approval. | P3 | Not run
GEN-01 | General | All web apps | Any | Mobile / tablet layout | Repeat P1 pages at phone width (~390px), tablet, and desktop. | No horizontal scrolling, overlapping or cut-off buttons; bottom nav works on phone. | P1 | Not run
GEN-02 | General | All web apps | Any | Browsers | Smoke test P1 flows in Chrome, Safari (iPhone) and Firefox/Edge. | Same behaviour in all browsers. | P2 | Not run
GEN-03 | General | All web apps | Any | Refresh & back button | On every portal page: refresh, and use browser back/forward. | No logout, blank page or error after refresh. | P1 | Not run
GEN-04 | General | All web apps | Any | Console errors & loading states | Keep DevTools Console open; throttle network to 'Slow 4G' on main pages. | No red console errors; loading skeletons instead of blank/jumping pages. | P2 | Not run
GEN-05 | General | Website | Any | Emails | Note every email you receive during testing (signup, reset, booking, registration, feedback). | Emails arrive, look correct, links work and point to the right environment. | P2 | Not run

## Summary
Test progress summary
Updates automatically from the Status column in 'Checklist'.
Module | Total | Pass | Fail | Blocked | Not run | N/A | % Passed (of run)
End-to-end flows
Auth
Public website
Cart & checkout
Customer account
Vendor portal
RM portal
Admin panel
General
TOTAL
P1 still failing or blocked
Release rule of thumb: this number must be 0.

## Bug Log
Bug ID | Test ID | Title | Steps to reproduce | Expected | Actual | Severity | App / URL | Account used | Browser / device | Screenshot / video link | Reported on | Status | Severity guide
BUG-001 | E2E-05 | Coupon total wrong in Razorpay popup | 1. Log in as customer 2. Add 2 services (₹500 each) 3. Apply SAVE10 4. Checkout | Popup shows ₹900 + fee | Popup shows ₹1000 + fee | High | Website /checkout | customer test account | Chrome 128 / Windows | (paste link) | 2026-09-22 | Open | Critical | Payment, booking or login broken; data lost or wrong money
[13 empty] | High | Main flow broken, no workaround
[13 empty] | Medium | Works but wrong/confusing; workaround exists
[13 empty] | Low | Cosmetic: text, spacing, colours